|  |
| --- |
| Project Status Report – [Project Report #1] |
|  |

|  |
| --- |
| Week Beginning: week 2(30/7/2012– 5/8/2012) |
|  |

|  |  |
| --- | --- |
| Status Legends: | |
|  | Everything is going well |
|  | Things Aren’t going the way they should be but it’s being managed |
|  | Something isn’t right and needs to be dealt with immediately |
|  |  |

|  |  |  |  |
| --- | --- | --- | --- |
|  | Last Week Goals: | Date | Status |
| 1 | *Gather Printers Requirements* | 31/7/2012 | 0% |
| 2 | *Create Look and Feel Prototype* | 2/7/2012 | 40% |
| 3 | *Create Class Diagrams* | 5/7/2012 | 0% |
| 4 | *Create Network framework* | 5/7/2012 | 20% |
|  |  |  |  |

|  |
| --- |
| Task Slippage: |
| *Printers requirements and class diagrams not yet gathered/started*  *Look and feel prototype done for server. Started but not yet complete for client application* |
|  |

|  |  |  |  |
| --- | --- | --- | --- |
|  | Next Goals: | Date | Status |
| 1 | *Gather Printers Requirements* | 7/7/2012 |  |
| 2 | Finish Look and feel prototype | 10/7/2012 |  |
| 3 | Create Network framework | 12/7/2012 |  |
| 4 |  | - |  |
| 5 |  | - |  |
|  |  |  |  |

|  |
| --- |
| Issues: |
| *Have been sick this week and not happy with built in controls for client application* |
|  |

|  |  |
| --- | --- |
| Risk: | Mitigation: |
| *Printer is unavailable for requirements elicitation* | Booking a time in to visit |
| *Continuation of being sick* | *Resting up and rescheduling tasks* |
|  |  |
|  |  |